## Sheet1
Sprint 1 - 03/02/2020 - 17/02/2020 | Aceptance Criteria | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Create User Database | Must contain user name | Connor Dawkins | 1 | 1 | 2020-02-05 | 14
Create Module/Timetable Database | Must contain module name | Connor Dawkins | 1 | 1 | 2020-02-05
Populate User Database | Must contain testable data | Gentian Gashi | 1 | 1 | 2020-02-06
Populate Module/Timetable Database | Must contain testable data | Gentian Gashi | 1 | 1 | 2020-02-06
Create Framework UI | UI must be capable of testing implemented functions | Gentian Gashi | 1 | 1 | 2020-02-08
Link User Database To Program | Program must be able to read from database | Tomas Porakis | 3 | 3 | 2020-02-08
Link Module/Timetable Database To Program | Program must be able to read from database | Tomas Porakis | 3 | 3 | 2020-02-08
Encrypt User Passwords | Hash must not be stored in the same database as the encyrpted password | Tovar Astrada | 3 | 1 | 2020-02-11
Implement Login Functionality | User can only log in when username and password are both correct | Tovar Astrada | 1 | 1 | 2020-02-11
Add Login UI | User must be able to enter their Username and Password | Tovar Astrada | 1 | 1 | 2020-02-11
[7 empty] | Sprint Burndown | 14 | 12 | 10 | 3 | 0
Sprint 2 - 17/02/2020 - 02/03/2020 |  | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Link User Database To Program | Program must be able to read from database | Connor Dawkins | 3 | 2 | 2020-02-20 | 20
Link Module/Timetable Database To Program | Program must be able to read from database | Connor Dawkins | 3 | 2 | 2020-02-20
Merge RegForm With Login Form | Reduce code duplication | Connor Dawkins | 1 | 1 | 2020-02-19
Update Login Code To Use Same Naming Scheme | Unify naming schemes for ease of programming | Connor Dawkins | 1 | 1 | 2020-02-19
Fix Bug Preventing MainForm From Loading | Critical bug introduced by LoginForm must be fixed | Connor Dawkins | 1 | 1 | 2020-02-18
Entering New Password For Username Overwrites Old Password | Critical security vulnerabilies must be removed | Connor Dawkins | 1 | 1 | 2020-02-18
Make Login Draw From User Database.XML File | Login must correctly read from User Databse | Connor Dawkins | 2 | 2 | 2020-02-25
Test Database - Class Linkages | Must import information from the database correctly | Connor Dawkins | 2 | 1 | 2020-02-25
Impliment Timetable UI | Must show current week timetable | Gentian Gashi | 2 | 2 | 2020-02-26
Design UI to Allow Admin to Edit Database | Must only be accesable by Admin Login | Gentian Gashi | 3 | 3 | 2020-02-26
Refine UI | UI must be easy for users to navigate | Gentian Gashi | 2 | 2 | 2020-02-27
Add A Help Button | Users should be able to easily find FAQ | Tomas Porakis | 1 | 1 | 2020-03-02
Add A Guide For Program Usage | Users should be able to see the intended method of use for program | Tomas Porakis | 1 | 1 | 2020-03-02
Test Database - Class Linkages | Must import information from the database correctly | Tovar Astrada | 2 | X
Implement Timetable Functionality | Users timetable should be correctly displayed when the user logs in | Tovar Astrada | 1 | X
[7 empty] | Sprint Burndown | 20 | 18 | 16 | 12 | 9 | 4 | 2 | 0
Sprint 3 - 02/03/2020 - 16/03/2020 |  | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Implement Timetable Functionality | Users timetable should be correctly displayed when the user logs in | Connor Dawkins | 3 | 2 | 2020-03-03 | 23
Edit User XML/Database to Allow Admin Identification | Program must be able to identify admins | Connor Dawkins | 2 | 2 | 2020-03-03
Delete Register Function From Login Page | Redundant features must be removed without causing bugs | Connor Dawkins | 1 | 1 | 2020-03-03
Add Functionality To Logout Button | Logout function must return UI to neutral state with no bugs | Connor Dawkins | 2 | 2 | 2020-03-10
Fix Bugs In Admin Functionality Forms | Admin Functionality must work completely without crashing | Connor Dawkins | 2 | 3 | 2020-03-14
Link Google Maps to Timetable | Correct map must open when user clicks on room in Timetable | Connor Dawkins | 2 | 3 | 2020-03-14
Fix & Refine Admin UI | Admin UI must have all necessary components for functionalty | Gentian Gashi | 2 | 2 | 2020-03-04
Fix Timetable Rows Bug | Timetable must work without major bugs | Gentian Gashi | 2 | 1 | 2020-03-06
Test Timetable Feature | The correct timetable must be displayed | Gentian Gashi | 2 | 2 | 2020-03-06
Test Admin User Editing Feature | User must be edited correctly, without error | Gentian Gashi | 2 | 2 | 2020-03-13
Fix Incompatible Code In Admin Functionality - Technical | Admin must have all necessary functionalities required | Gentian Gashi | 3 | 3 | 2020-03-13
Test Login Feature | Login and Logout featrues must be tested | Tomas Porakis | 1 | X
Update Help Box | Help box should have information for all features | Tomas Porakis | 1 | X
Create Tooltips For UI | Most UI elements should have a tooltip | Tomas Porakis | 2 | X
Test Admin Database Editing | Admin Database Editing must work without critical issue | Tomas Porakis | 1 | X
Implement Admin Functionality | Admin must be able to edit extisting user/timetable database and add new users | Tovar Astrada | 2 | X