## Sheet1
Sprint 1 - 03/02/2020 - 17/02/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Create User Database | Connor Dawkins | 1 | 1 | 2020-02-05 | 8
Create Module/Timetable Database | Connor Dawkins | 1 | 1 | 2020-02-05
Implement Timetable UI | Connor Dawkins | 1 | X
Populate User Database | Gentian Gashi | 1 | 1 | 2020-02-06
Populate Module/Timetable Database | Gentian Gashi | 1 | 1 | 2020-02-06
Create Framework UI | Gentian Gashi | 1 | 1 | 2020-02-08
Link User Database To Program | Tomas Porakis | 3 | 3 | 2020-02-08
Link Module/Timetable Database To Program | Tomas Porakis | 3 | X
Encrypt User Passwords | Tovar Astrada | 3 | X
Implement Login Functionality | Tovar Astrada | 1 | X
Add Login UI | Tovar Astrada | 1 | X |  |  | Sprint Burndown | 17 | 15 | 13 | 9 | 3
Sprint 2 - 17/02/2020 - 02/03/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Link User Database To Program | Connor Dawkins | 3 | 2 | 2020-02-20 | 20
Link Module/Timetable Database To Program | Connor Dawkins | 3 | 2 | 2020-02-20
Merge RegForm With Login Form | Connor Dawkins | 1 | 1 | 2020-02-19
Update Login Code To Use Same Naming Scheme | Connor Dawkins | 1 | 1 | 2020-02-19
Fix Bug Preventing MainForm From Loading | Connor Dawkins | 1 | 1 | 2020-02-18
Entering New Password For Username Overwrites Old Password | Connor Dawkins | 1 | 1 | 2020-02-18
Make Login Draw From User Database.XML File | Connor Dawkins | 2 | 2 | 2020-02-25
Test Database - Class Linkages | Connor Dawkins | 2 | 1 | 2020-02-25
Impliment Timetable UI | Gentian Gashi | 2 | 2 | 2020-02-26
Design UI to Allow Admin to Edit Database | Gentian Gashi | 3 | 3 | 2020-02-26
Refine UI | Gentian Gashi | 2 | 2 | 2020-02-27
Add A Help Button | Tomas Porakis | 1 | 1 | 2020-03-02
Add A Guide For Program Usage | Tomas Porakis | 1 | 1 | 2020-03-02
Issue 1 | Tovar Astrada | X | X
Issue 2 | Tovar Astrada | X | X |  |  | Sprint Burndown | 20 | 18 | 16 | 11 | 8 | 4 | 2
Sprint 3 - 02/03/2020 - 16/03/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Issue 1 |  | X | X |  | 0
Issue 2 |  | X | X
Issue 3 |  | X | X
Issue 4 |  | X | X