## Sheet1
Sprint 1 - 03/02/2020 - 17/02/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Create User Database | Connor Dawkins | 1 | 1 | 2020-02-05 | 8
Create Module/Timetable Database | Connor Dawkins | 1 | 1 | 2020-02-05
Implement Timetable UI | Connor Dawkins | 1 | X
Populate User Database | Gentian Gashi | 1 | 1 | 2020-02-06
Populate Module/Timetable Database | Gentian Gashi | 1 | 1 | 2020-02-06
Create Framework UI | Gentian Gashi | 1 | 1 | 2020-02-08
Link User Database To Program | Tomas Porakis | 3 | 3 | 2020-02-08
Link Module/Timetable Database To Program | Tomas Porakis | 3 | X
Encrypt User Passwords | Tovar Astrada | 3 | X
Implement Login Functionality | Tovar Astrada | 1 | X
Add Login UI | Tovar Astrada | 1 | X |  |  | Sprint Burndown | 17 | 15 | 13 | 9 | 3
Sprint 2 - 17/02/2020 - 02/03/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Link User Database To Program | Connor Dawkins | 3 | 2 | 2020-02-20 | 8
Link Module/Timetable Database To Program | Connor Dawkins | 3 | 2 | 2020-02-20
Merge RegForm With Login Form | Connor Dawkins | 1 | 1 | 2020-02-19
Update Login Code To Use Same Naming Scheme | Connor Dawkins | 1 | 1 | 2020-02-19
Fix Bug Preventing MainForm From Loading | Connor Dawkins | 1 | 1 | 2020-02-18
Entering New Password For Username Overwrites Old Password | Connor Dawkins | 1 | 1 | 2020-02-18
Issue 3 |  | X | X
Issue 4 |  | X | X
Sprint 3 - 02/03/2020 - 16/03/2020 | Assigned To: | Estimation Points | Completed Points | Date | Total Points
Issue 1 |  | X | X |  | 0
Issue 2 |  | X | X
Issue 3 |  | X | X
Issue 4 |  | X | X